## Sheet2
MCI Project Weekly Time Sheet
Team | 8 | Student ID | a1699186 a1692118 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task |  | Outcome/Next action
Monday | 24/4/2017 | 13:00 | 16:00 | 4 | Prepare project to show Christoph and fix server. | Individuals can use a link to visit our website in their own computers. | We cannot use Amason, since it has data limit.
Wednesday | 26/4/2017 | 13:00 | 16:00 | 3 | Try to change a web server. |  | We changed Amason to digitalocean, it worked.
Thursday | 27/4/2017 | 11:00 | 15:30 | 4.5 | Fix digitalocean |  | We cannot use digitalocean, since the data that we visit is too huge, digitalocean think we are the hacker, so it forbids us to use.
Friday | 28/4/2017 | 3:00 | 17:00 | 2 | Sometimes we cannot extract picture informations form readmefiles, so we need to fix it. |  | The function about picture is fixed.
Saturday | 29/4/2017 | 11:00 | 18:00 | 7 | Fix some errors about functions, such as repeat links number. |  | Next action for us is to work out a way that we can use servers.
|  |  | Total | 20.5