## Sheet2
MCI Project Weekly Time Sheet
Team | 8 | Student ID | a1699186 a1692118 |  |  | Week starting: | 9
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 8/5/2017 | 11:00 | 17:00 | 6 | Fix the cloud server | Depending on the client additional requirement | We cannot use cloud server since all companies will forbid our operations, so we can only use the lost host to vist our website.
Thursday | 11/5/2017 | 13:00 | 17:00 | 4 | Fix the function of extracting the URLs | Depending on the requirement | The website still cannot extract URLs since the result always shown zero, we need to still work on it.
Friday | 12/5/2017 | 13:00 | 17:00 | 4 | Make the extracted titles list in order | Depending on the client additional requirement | The titles list in order from large to small of the amount
Sunday | 14/5/2017 | 10:00 | 18:00 | 8 | Beautify the interface | Depending on the requirement | We use bootstrap to beautify the interface, we spend a lot of time to fix the problem that the background image cannot display, since we put the background image into a wrong folder.
|  |  | Total | 22